## Sheet1
| Meetings | Manasvi Dobariya |  |  | Darshak Chavda |  |  | Yesha Ajudia |  |  | Kartavi Baxi |  |  | Dishita Madani |  |  | Shivani Kadam |  |  | Aisha Nagrecha |  |  | Nisarg Thoriya
|  | What did you do yesterday? | What will you work today? | Did you have any obstacles? | What did you do yesterday? | What will you work today? | Did you have any obstacles? | What did you do yesterday? | What will you work today? | Did you have any obstacles? | What did you do yesterday? | What will you work today? | Did you have any obstacles? | What did you do yesterday? | What will you work today? | Did you have any obstacles? | What did you do yesterday? | What will you work today? | Did you have any obstacles? | What did you do yesterday? | What will you work today? | Did you have any obstacles? | What did you do yesterday? | What will you work today? | Did you have any obstacles?
Sprint -1 | Meeting-1 (27/02/2021) Identifying features | Receiver Related feature identification | Finding features related to Hospital | Less knowledge of the field | - | Listing the features related to Application | - | Searched for the features related to blood donation | Search for some of the existing applications and its features | - | Searched different features of blood donation | Search some existing Blood donation related application | - | Feautures identification required for donation | Feauture identification for receiver | No obstacles faced | Identified features on donation module | Identification of features - user interface | null | Checking the feasblity of all features | Prioritizing the features according to our needs | - | Hospital Related feature Identification- Listing | Finding Features related Application Process and tracking | null
| Meeting-2 (01/03/2021) Identifying Stakeholders | Listing stakeholders | Search business related stakeholders | - | Searching about stackholders | Listing the potential stackholders | Not much information about stackholders | Know who can be the stakeholders | How will those stakeholders play a role in the system | Was not sure initially about how can a hospital be fit to our applicaiton | Identifying Stakeholders | Understand the imporatnce of stackholders in the system | Less knowledge about stackholders | Looked up on identifying stakeholders through examples | Identifying stakeholders for our project | Had some conflicting view points while discussing with the team | Searched about stackholders | Selection of stackholders | Cross verification with team mates | Researching about the stakeholders and look at some examples | Listing down the feasible stakeholders | Consensus of all team members on stakeholders | Searching about stackholders | Listing the potential stackholders | less knowledge about stackholders
| Meeting-3 (04/03/2021) User Interface Features | Website common features identified | Relating it to problem at hand | Finding appropriate techniques | Getting motivation from other blood donation application | Listing important feautes related to Application | - | Listing some common interface features for the application | How can the listed interface features play a role in our application | Merging all the features in one | Seacrched some athor blood donation application and making list of common features | Verify features with team | Merging all features | Looked up on different websites for designing purpose | Worked specifically for blood donation websites | Required a lot of brainstorming while thinking of a design | Searched more application of blood donation | Collection of features from other applications | How to merge all ideas | Identify the users and make user friendly and sensitive interface | Prioritize the features according to users | - | Getting motivation from other blood donation application | Listing the impoertant User interface features | cross validation with teammates
| Meeting-4 (06/03/2021) Use case Diagram | Identifying external Users | Identify use cases | Connections of Use cases | Identifying actors for designing Use Case Diagram | Understanding use cases | Understanding use case diagram | Looked at some use case diagrams | Identify actors, use cases, and their connections | Connecting the actors with their use cases | Understood use case diagram by checking some document | Working on the use case diagram of our project | Identifying connections | Understood the purpose of use case diagram | Working on use case diagram for the project | Making an online diagram through the tools was a bit difficult | Understood rules of the diagram | Understanding project idea and mapping into use case diagram | Different rules on diffierent sources | Identify the use cases for all users | Establish relations between the use cases | Got confusion in include and extend relations | Identifying actors for designing Use Case Diagram | Identifying use-cases for our problem statement | finding propere tool
| Meeting-5 (10/03/2021) ER Diagram | Conceptual ER diagram development | Logical ER development | Understandin crow's foot notations | Understood the rules for ER Diagram | logical ER diagram for our problem statement | Difference between logical and physical ER Diagram | Had an understanding of difference between the three levels of ER diagrams and their rules | Logical and Physical ER diagram | Match the datatypes of attributes with the used database framework | Understood ER diagram by checking some document | Physical ER delopment | Found diificulties for some relations | Recalled what we had taught about ER diagram in the class | Mapping of concepts of our project into ER diagram | Found difficult to establish 2/3 relations | Understood rules of the diagram | Understanding project idea and mapping into ER diagram | Physical vs logical diagram understanding | Define the entities and find online tool best for E-R diagram | Define the relations between the entities and define cardinality | Confusion came in storing the hospital json file as an entity | Understood the rules for ER Diagram | logical ER diagram for our problem statement | Difference between logical and physical ER Diagram
| Meeting-6 (11/03/2021) DFD(Context) | Identified all external entities | Connecting Hospital Entity with System | - | Identifying external entities | context diagram for our problem statement | - | Examples of the levels of DFD | Identify external users/entities to the system and context diagram | - | Identify external entities | Implement DFD for some module | - | Understandind the concept of data flow - why is it important | working on DFD for project | No obstacle | Understood DFD from diferent resources | Implented DFD for a small module | null | Determining the best online tool for DFD Diagram | Defining the input output and processes | Difficult to create symbols in MIRO | Identifying external entities | context diagram for our problem statement | defining connections
| Meeting-7 (15/03/2021) DFD -Level-1 | Expanding main system into different processes | Work on connection of Receiver entity with process | Database Selection |  | Context to level 1 DFD |  | Rules for expanding DFD to level 1 | Identify the processes | - | Read about expanding DFD to level 1 | Work on connection with donor entity of the process | Process identification | Understanding of expanding DFD 0 to DFD 1 | Extended the level 0 diagram | Queries regarding the entities | Understood system boundary concept | Extension of context diagram | Some doubts regarding datastore and external entity | Segregating the processes and features for each user | Creating the Donor and Hospital DFDs | Create symbols and manage space | Identifying system into processes | DFD level-1 for our problem statement | some doubts regarding processes
| Meeting-8 (17/03/2021) DFD-Level-2 | Receiver Processes Expanded into sub processes | Database connections with Processes | Dependencies Identification | Analysis on expanding level 1 to 2 DFD | Level 1 to Level 2 DFD |  | Searched for some level 2 DFDs | Expand the processes and connect database | Expand the processes in the ratio of 1:5 and identify dependencies | Read about expanding level 1 to level 2 | Working on dependencies | Facing diificulties for dependencies | Linking DFD 1 with DFD 2 through examples given in the class | Working on level 2 diagram for donor | Found difficulties in resolving dependencies | Conections and links between context - level1 | Extension of level-1 | Dependencies error | Adding more details to the features | Connected those processes to appropriate databases | Had to repeat databases and manage spaces to make it more readbale | Donation process expand in sub-process | DFD level-2 for donation process in our problem statement | doubts regarding datastore
| Meeting-9 (19/03/2021) Sequence-diagram | Research on Sequence Notations and tools | Defining different screens for donor module | Selecting best tools for diagram | Level 2 DFD | gathering infomation about sequence diagram |  | Read through the articles for Sequence Diagram | Start with Donor module | Choose a proper tool for sequence diagram | Understood sequence diagram by checking some document | Work on donor module | - | Understanding the need of sequence diagram | Implementing sequence diagram for donor | Brainstorming while fixing the functionalities for donor module | Understood the concept of sequence diagram | searched more about lifeline | Doubt on lineline destrruction | Finding the best tool for sequence diagram | Making sequence diagram for Donor interface | It was difficult to find the right online tool | Research On Sequence Diagrams | more search regarding Sequence Diagram | Which tool to choose for Sequence DIagram
| Meeting-10 (21/03/2021) Sequence-diagram | Alternative Conditions Defined | Donor Module Sequence lifeline Connections | - | gathering more info about sequence diagram | sequence diagram of user module |  | Rough sketch of sequence diagram on pen paper | Complete the donor module of sequence diagram | Defining alternative conditions | - | Work on hospital module | Facing difficulties while fixing the functionality | verification of sequence diagram - donor module | implementing sequence diagram for hospital | resolving functionalities | Conceptual understanding | implemented sequence diagram for donation module | Dependency solving | Determined the flow of hospital interface | Making the sequence diagram for hospital interface | making sure that only one lifeline is active at a time | Implementing sequence diagram for Reciever | verification of sequence diagram for Reciever | doubt on objects
| Meeting-11 (23/03/2021) Sequence-diagram | Receiver module sequence done | Review the whole diagram | DFD and sequence tracebility | sequence diagram | sequence diagram of Hospital module |  | Started Receiver module | Hospital module | Keep a track of sequence and merge all the modules | Verify receiver module sequence | Complete remaining work of hospital module | Facing difficulties while fixing the functionality | verification of sequence diagram - hospital module | merging sequence diagram for entire system | Solving the dependencies between each module | selected tool for making diagram | Implemented sequence diagram for hospital module | Capturing the whole system diagram into one image was difficult | Making the Reciever interface | Reviewing the sequence diagram and checking with the team members | Managing the lifelines for all users | Alternative conditions defined | verification for alternative conditions | some doubts regarding alternative conditions
| Meeting-12 (24/03/2021) Frontend design plan | Reviewed related websites for better design | Identify navigation and sidebar related design | Difficult to find one optimum design | sequence diagram | Analysis to implement listed features into design |  | Looked for different related applications and websites | Some basic static elements for each, donor, receiver and hospital | - | Looking some website for designing | Identify nevigation and sidebar related design | - | Looking for various languages used for frontend | Finalising the language for our project | Clash of opinions | Searched some best designs for blood donation application | Suggested some good ideas and selected the design for he project | null | Determine the flow of donor and hospital interface | Determine the flow of Receiver Interface | - | Searching different website for design | identify basic elements for design | no obstacle
| Meeting-13 (25/03/2021) Figma design | Login and signup design finalisation | Navbar and sidebar design | Getting familiar with tool | Basic idea of design theme | Login and Register Page Design |  | Getting familiar with the tool | Design of login and signup page | - | - | Making sample project | - | Started with a small design in figma | Making a sample home page for project | No obstacles | learned how to use figma | Figma login module design | searching symbols and shapes for the first time was difficult | Design the navigation and sidebar for all pages | Designing and reviewing the home screen and make a news and events section | Conflict with group members for homescreen design | Design for sidebar,navbar | designing home-screen | getting familier with figma
| Meeting-14 (26/03/2021) Figma- design | About us page design | - | - | Dashboard and Homepage | Dashboard and other page design |  | Final design of homepage and dashboard | About Us and Contact Us design | - | Login Design | Design contact us and about us | - | Final homescreen and dashboard design | Design for hospital module | No obstacles | Login signup modules were done | Donation module design in figma | requirment fills at the first point was difficult task | Designing the general pages after login of user | Reviewing the designs and suggesting changes for other design pages | - | Design for Dashboard | changes in Dashboard design | searching different icons and elements
Sprint 2 | Meeting-15 (30/03/2021) Figma- design | Dashboard Design parts | Dashboard optimiztion and sidebar and navbar add | Content Identifying | Hospital module pages design | Hospital module pages design |  | Design Why Donate Blood | Hospital module design | - | Completed contact us and about us design | Help in some hospital module design | - | Working on the hospital module | Hospital module was completed | No obstacles | Donation module was done | Improvment in design and receiver module | null | Make web pages designs for hospital Interface | Reviewing the designs and making it more user friendly | - | Design for Hospital Dashboard | Design for Hospital Post events page | searching different icons and elements
| Meeting-16 (01/04/2021) Coding of Login and Signup | Firebase Connection search | Authentication window setup | Understanding firebase | Coding of Login page | Updating style by changing in CSS | solving stying errors | Understanding working of firebase and ReactJs | Signup and login page in React | Connecting with firebase and npm installation errors | Understanding working of firebase and ReactJs | Login page in react | npm installation errors | Basic design in figma and learning ReactJs | Implementing the login page in ReactJs | Package installation errors | made a Git repo | Initialised the project | git errors | Determined the necessary fields from the user | Establishing connection with firebase and react | Was not able to connect properly | Understanding working of React | code for navbar | npm installation errors
| Meeting-17 (05/04/2021) Resolving errors | Testing Signup and login | Login error resolve | - | minor CSS changes and fixes | Donor Profile and Validation |  | Test signup and login for each user | Give proper validation messages for each error | Sign in not working after sign out | Solve npm installation errors | Errors in signup page solve | Error during firebase authantication | Google authentication added for login | Designing of other pages | Git upload errors | Git errors solved | Login signup code | erroes during firebase authentication connection | Did debugging and reviewed code for user authentication | Discovered the bug and made appropriate changes | No error was shown on console but user was not registered in firebase | testing for signup | resolving errors for signup page | null
| Meeting-18 (07/04/2021) Test cases creation | Created test-cases for Receiver Module | Create test case for receiver request module | Learning test-case making |  |  |  | Learn types of tests and how to write test cases for an application | Wrote unit test cases for each form to be filled in the application | Integration test cases for each button leading to navigation | Understand types of test cases and their meaning | Unit case for login and signup | - | Package installation errors solved | Backend - creating a demo project on firebase | Learning firebase | Errors in login signup solved | Firestore connection understanding | error in building firebase project | Created test cases for user sign up and sign in | Created test cases for hospital sign in and sign up | Repeated alert messages in a loop while validating password length | create test-case for login page | create test-case for login page | learning test-case making
| Meeting-19 (10/04/2021) Donation module | Retrieved JSON file of hospital and city | Display Hospital in selected city in dropdown | Getting selected item from dropdown | Hospital navbar fixed | Improve UI by updating CSS |  | List and verify what medical details are required for donating blood | Listing validations for each possible field in donor profile | Implement the validations and resolve errors regarding the same | List requirments of medical details for donate blood | Design of medical profile for donor | Errors | Updating the project and listing the donors details requirement | Frontend design for donor details | ReactJs errors | Donation module js file creation | Coding, validations in donation module | Submit button handle error | Created the donor profile form and inserted validations in it | Checking the eligiblity of the donor and if eligible send application to hospital | Extracting hospitals for the given city from json file and display in drop down | code for sidebar and form | code for list | allignment using css
| Meeting-20 (11/04/2021) Donation errors | Testing module with test-cases | Fixing Donation errors | - | Sidebar fix | Donate Blood alignment and style |  | Continued error solving for donation module | Resolve the remaining errors and final check for validations | - | Resolving previous errors | Testing module with test-case | - | Null | Resolving ReactJs errors | No obstacles | Error solving | test modules creation | null | Drop down values were not getting stored in database | Solving the error of selected hospital not getting stored in firebase | - | errors in sidebar | Resolving the React errors | No obstacles
| Meeting-21 (12/04/2021) Receiver Module | Configured Receiver Database | Get data from form and store it in database | Data Formatting |  | Hospital dashboard changes |  | Listing validations for all possible fileds in receive request form | Implement the validations and resolve errors regarding the same | Validating country code in contact number field | Understand validations of request module | Implement validations of receiver module | Getting some error | Working on receiver module | Figma design for receiver screens | No obstacles | Understanding module | Submit button handle in receiver module | validations understanding | Made receiver request form and applied validations | Add emergency donors list and include the feature of request updation | Passing email to view requests page | code for recieve blood form | code for donors list | validations understanding
| Meeting-22 (14/04/2021) Receiver module errors | Tested Receiver module for error | Add Received donations to dashboard and increase count | - | dashboard changes | Receiver Request |  | Continued solving errors for receiver module | Tested the form with every test case and align the error messages properly | - | Solve previous error of receiving module | Solving errors | Difficulties in solving errors | Null | Null | Null | Firestore error solving | null | null | Errors in extracting hospital values from json file and storing in firebase | Creating request updation buttons and its implementation | Displaying all the requests and uniquely identifying them | errors while fetching donors list | error while submitting the recieve request | learning about React Router DOM
| Meeting-23 (16/04/2021) Coding of User Inteface | Navbar and sidabar alignments and symbols done | - | - |  |  |  | Collect the content for contact us page | Design js and css files for Contact Us page | Alignment in CSS | - | Request Blood css add | Difficulties in CSS alignments | Null | Working on Figma designs | No obstacles | null | Track application module | null | Creating the html and css files for frontend | Making the interface more attractive | Alignment different for different interfaces | adding css files for dashboard | adding css for homescreen | allignment using css
| Meeting-24 (18/04/2021) Developing UI | UI of form of receiver developed | Dashboad UI development | Learning CSS and alignment for all window size |  | changes in banner and other components |  | Collect the content for about us page | Design js and css files for About Us page | Alignment in CSS | - | - | - | Finding information on why one should donate blood and creating a simple html css for the same | Implementing it in ReactJs | Error while creating a popup | Design and frontend testcase | Changes in UI | Css errors and alignment issues | Add pictures and banners for all interfaces | Include the about us and contact us pages | - | reciece request css file | donate blood css add | allignment using css
| Meeting-25 (20/04/2021) Hospital Module Coding | Development of display count of successful donations | Display successful donations list from dashboard | Disabling button on dashboard when 0 count |  | Add Events and See all events |  | Giving links to hospital dashboard and verify proper navigations | Update the status of test cases of completed modules | - | - | - | - | Solving the popup error in ReactJs | Re structuring Hospital module design | No obstacles | Hospital module understanding | Hospital Login/ signup functionality | checking licence number with json file was difficult | Add events feature of hospital, store events of registered hospital | Update application feature of hospital and maintain history | While storing image in firebase | understanding elements in hospital module | hospital sign-up functunality | null
| Meeting-26 (21/04/2021) Hospital Module Coding | Appointments module for datewise appointments built | Adding Complete donation module | React Calender learning | Updating Events page | Add Events and See all events |  | Check the working of donation completed button | Solve the error in donation completion | - | - | - | - | Re structuring use case diagram - small changes | Re structuring er diagram - small changes | No obstacles | Hospital appointment module understanding | Show appointment list of the selected date | firebase errors solving | Adding the show appointments feature | Display all the Successful donations | Passing the license of hospital in every page | adding elements in hospital post events page | Appointments module for datewise appointments | learning React calandar
| Meeting-27 (23/04/2021) Resolving Hospital errors | Testing hospital appointments module | Fixing errors and bugs | - | Request Blood module | Request Blood module |  | Check for proper error messages in popup | Suggest changes for some to the team | - | - | Helping in solving errors | - | Cloning the entire work done and made some small changes | Solving react errors | No obstacles | Firestore errors solving | Testing case and successful donation on hospital interface | null | solved the error in displaying the calendar and selecting date | Making the donation complete of a donor | - | Resolving errors in react calandar | resolving errors for events page | null
Sprint 3 | Meeting-28 (26/04/2021) Integration testing | Tested user navigations on dashboard | Fix wrong navigation routes | Dependencies resolution | About us and Contact Us for user | Why Donate Blood update |  | Learn the difference between unit tests and inegration tests | Write integration test cases for the application | A navigation button of complete donation not working | Understaing the concept of integration testing and start working on it | Navigating them with the help of navbar - proper linking | Error bcoz og some html tags | Working on contact us, about us and why donate blood | Navigating them with the help of navbar - proper linking | Errors due to some html tags like br tag was not working properly | Test cases of track application | Integrate Book slot | Errors handling book slot | Gaining the idea of integration testing | Look at several examples and ways to implement | errors for the different navigation bar of hospital and user | understanding integration testing | writing integration testing | how to wirte integration test
| Meeting-30 (2/05/2021) Frontend alignment | Events and other modules alignment | Documentation work | - | Finding ideas for Hospital Banner | Updating Hopital dashboard banner |  | - | - | - | Review the project | Review the project | - | Reviewing the project if anything was left for designing | reviewing the figma designs | No obstacles | Discussion of errors in book slot | Frontend discussion and improvement suggested | null | Calendar for book slot and appointment | Inserting a slider for the registered hospital | Alignment of 2 events in a row due to size difference | change in css for proper alignment in hospital events page | frontend discussions and reviewing project | finding minor css changes
| Meeting-31 (3/05/2021) Remaining Documentation | Construction and definition of done document | Requirements tracebility matrics updates | Finding related documents online | working on About us and Contact Us for Hospital | About Us and Contact Us updated |  | Verified the test cases, whether any test case is left | Define functional requirements along with purpose, response, and associated fucntional requirements of each function | - | Worked on requirments understanding documentation | Working on unit case documentation | - | Working on Requirements undersatnding documentation | Completing requirements understanding document | No obstacles | null | Testing documentation | Finding errors | Final touch on regular meeting document | Make changes in requirement document by reviewing the diagrams | - | null | working on requirements understanding document | null
| Meeting-32 (6/05/2021) Testing errors solved | Some basic navigation routes fixed | Deployment work | - | working on verification page | verification page updated |  | Update the status of each test case after verfying its working in the application | Check the navigation errors | - | Remaining part of unit case documentation | Working on integration test-case documentation | - | Working on test cases documentation | Completing test cases document | No obstacles | Some basic navigation routes fixed | Links fixed | Errors | Errors related to appointment display | Fixing the missed redirections were missed | - | some navigation routes fixing | updating minor css changes | finding minor errors
| Meeting-33 (7/05/2021) Deployment | Deployment of site on firebase | - | Resolving local errors | Updating minor CSS changes | Resolving minor issues |  | Complete the design documentation | Final check of every function | - | Working on some parts of test case documentation | Working on designing documentation | - | Working on design documentation | Combinig all the documents | No obstacles | Documentation | Deployment work | null | Checking all modules and all buttons | - | - | updating minor css changes | working on design document | null